E-COMMERCE PROJECT PROPOSAL

UrbanFit BD

Web Design and Development for Freelancing – Level 5
Job 04: Prepare Project Proposal

| Project Information | Details |
| --- | --- |
| Client | UrbanFit BD |
| Project Type | Fashion E-Commerce Website |
| Preferred Approach | Open-source – WooCommerce / WordPress |
| Initial Client Budget | BDT 1,20,000 |
| Initial Proposed Budget | BDT 1,65,000 |
| Initial Delivery Target | 35 days |
| Revised Client Target | Approximately BDT 1,32,000 |
| Revised Delivery Target | 25 days |
| Notifications | Email only in Phase 1; SMS moved to Phase 2 |
| Prepared By | Md. Golam Maula |
| Date | 12.09.2026 |

Confidential Project Proposal

# 1. Requirement Gathering & Client Questionnaire

The following questions are used to confirm the client’s business, technical and delivery requirements before development.

| Area | Question / Requirement | Confirmed Understanding |
| --- | --- | --- |
| Business | What is the main purpose of the website? | Sell UrbanFit BD fashion products online before the Eid sale. |
| Products | What product information is required? | Product name, images, price, category, size/variant, stock and description. |
| Catalog | How should customers browse products? | Categories, product search, filters and product detail pages. |
| Orders | What purchase flow is required? | Cart → checkout → payment/COD → order confirmation. |
| Payment | Which payment methods are required? | Mobile banking/payment gateway and Cash on Delivery. |
| Shipping | Which delivery service is required? | EMS shipping integration / shipping workflow. |
| Notifications | How should customers receive updates? | Email notifications in Phase 1; SMS removed from current scope. |
| Security | What security is required? | HTTPS/SSL, secure admin access, backups and basic hardening. |
| Platform | What technology is preferred? | Open-source WooCommerce/WordPress for lower license cost and flexibility. |
| Timeline | What is the revised deadline? | 25 days after client feedback. |
| Budget | What is the revised target? | Approximately BDT 1,32,000. |
| Support | What happens after launch? | Warranty/support period and maintenance under the service agreement. |

# 2. Requirement Assessment & Confirmed Summary

## 2.1 Clarity

The major features are specific: catalog, cart, checkout, payment, COD, EMS shipping, email notifications and SSL.

The revised scope is measurable through acceptance testing of each agreed feature.

## 2.2 Feasibility

WooCommerce is suitable because it provides established e-commerce functions with lower licensing cost and high customization.

The original 35-day plan is feasible; the revised 25-day plan is achievable by reducing scope, prioritising core features and increasing development focus.

## 2.3 Completeness

Hosting/domain, SSL, payment setup, tools/software, testing, deployment and post-launch support are included in planning.

SMS notification is not included in the revised Phase 1 scope and is moved to future improvement.

## 2.4 Confirmed Requirement Summary

| Requirement | Initial Scope | Final Confirmed Scope |
| --- | --- | --- |
| Platform | Open-source WooCommerce/WordPress | WooCommerce/WordPress |
| Product catalog | Required | Required |
| Cart & checkout | Required | Required |
| Mobile banking/payment | Required | Required |
| Cash on Delivery | Required | Required |
| EMS shipping | Required | Required |
| Email | Required | Required |
| SMS | Required | Removed; Phase 2 |
| HTTPS/SSL | Required | Required |
| Launch | 35 days | 25 days |
| Budget | Client: BDT 1,20,000 | Target: ≈ BDT 1,32,000 |

Assessor/client sign-off: __________________________    Date: ______________

# 3. Technology Options & Recommendation

| Option | Advantages | Limitations | Suitability |
| --- | --- | --- | --- |
| Open-source – WooCommerce / WordPress | Lower licensing cost; flexible; large plugin ecosystem; full control; easy customization. | Requires hosting, maintenance and security management. | Recommended |
| Close-source – Shopify | Fast launch; managed hosting; simpler maintenance. | Recurring subscription; app costs; less control/customization. | Alternative |

Recommendation: WooCommerce is selected because UrbanFit BD prefers an open-source solution and needs a realistic balance of cost, customization and e-commerce functionality.

# 4. Initial Project Proposal – 35 Days

## 4.1 Background of the Project

UrbanFit BD is a fashion retailer planning to move online before the Eid sale. The project will deliver a responsive e-commerce website that allows customers to browse products, place orders, choose payment methods and receive order information by email.

## 4.2 Project Objectives

Launch a professional and mobile-friendly UrbanFit BD online store.

Provide a complete product catalog and shopping cart experience.

Enable mobile banking/payment gateway and Cash on Delivery.

Support EMS shipping workflow and email notifications.

Provide HTTPS/SSL and basic security measures.

Deliver an administrator-friendly system for products and orders.

## 4.3 Project Schedule – Initial 35 Days

| Period | Milestone / Activities | Deliverable |
| --- | --- | --- |
| Days 1–7 | Requirement confirmation, sitemap, UI planning, WordPress/WooCommerce setup. | Approved requirements + initial design |
| Days 8–14 | Theme customization, homepage, categories, product pages and responsive layout. | Catalog interface |
| Days 15–21 | Cart, checkout, customer details, COD and payment gateway setup. | Working purchase flow |
| Days 22–28 | EMS shipping, email notifications, SSL/security, admin configuration. | Integrated store |
| Days 29–35 | Testing, bug fixing, content checks, client review, training and deployment. | Production website |

## 4.4 Functional Requirements

Responsive homepage and navigation

Product categories and catalog

Product search and basic filters

Product details with images, price, size/variant and stock

Shopping cart and quantity management

Checkout and customer information

Mobile banking/payment gateway integration

Cash on Delivery

EMS shipping integration/workflow

Order management from admin panel

Email order/notification system

HTTPS/SSL and basic security

## 4.5 Risk Management

| Risk | Impact | Mitigation / Response |
| --- | --- | --- |
| Mobile banking API integration delay | High | Confirm gateway credentials early; keep a 1-week contingency in the schedule; use a tested sandbox first. |
| Client scope changes mid-project | Medium/High | Use a written change-request policy; changes may affect cost and deadline. |
| Eid deadline pressure | High | Prioritise core catalog and ordering features; use phased launch if required. |
| Content/product data delay | Medium | Provide a structured product data template and agree on content deadlines. |
| Security or plugin conflict | Medium | Use compatible plugins, staging tests, backups and SSL before launch. |

## 4.6 Initial Project Budget

| Cost Item | Calculation | Amount (BDT) |
| --- | --- | --- |
| Development effort | 200 hours × 500 | 1,00,000 |
| Hosting + domain | Fixed estimate | 15,000 |
| SSL certificate | Fixed estimate | 5,000 |
| Payment API setup | Fixed estimate | 20,000 |
| Tools / software | Fixed estimate | 10,000 |
| Subtotal |  | 1,50,000 |
| Contingency | 10% of subtotal | 15,000 |
| Initial Total |  | 1,65,000 |

Note: The initial proposed total is higher than the client’s stated budget of BDT 1,20,000; negotiation and scope adjustment are therefore expected.

## 4.7 Resources

Team: Project manager, web developer, UI/content support and client representative.

Technology: WordPress, WooCommerce, compatible theme/plugins, payment gateway and EMS shipping workflow.

Infrastructure: Domain, web hosting, SSL certificate, backup and staging environment.

Tools: Code editor, browser, spreadsheet, documentation tools and communication tools.

## 4.8 Overall Benefits for UrbanFit BD

Reach customers online and support Eid sales.

Provide 24/7 product browsing and ordering.

Reduce manual order handling through online order management.

Improve customer convenience with online payment and COD.

Create a scalable foundation for future mobile app, SMS and marketing features.

## 4.9 Future Improvements – Phase 2

SMS order and delivery notifications.

Customer loyalty/reward features.

Advanced reporting and sales analytics.

Mobile application or PWA.

Advanced marketing automation and promotional campaigns.

## 4.10 Service Agreement

| Item | Agreement |
| --- | --- |
| Scope | Only the confirmed requirements listed in this proposal are included. |
| Payment | Suggested: 40% advance, 40% after core e-commerce functions, 20% on final delivery. |
| Delivery | Initial plan: 35 days; final revised plan: 25 days after scope revision. |
| Client Responsibilities | Provide logo, product data, images, payment/EMS credentials and timely approvals. |
| Change Policy | New features or major revisions require a written change request and may change price/deadline. |
| Warranty | 30 days of corrective support for defects related to the delivered scope. |
| Maintenance | Ongoing maintenance, content updates and third-party service fees are separate unless agreed. |
| Third-party Costs | Gateway charges, domain renewal, hosting renewal and paid plugins/services are subject to provider pricing. |

# 5. Client Feedback After Initial Proposal

| Client Feedback | Required Action |
| --- | --- |
| Reduce total cost by 20%. | Reduce scope and/or development hours and adjust supporting costs while maintaining essential functionality. |
| Launch in 25 days, not 35 days. | Compress milestones, prioritise core features and remove non-essential work from Phase 1. |
| Remove SMS – keep Email notification only. | Remove SMS from current functional requirements and move it to Phase 2/future improvement. |

# 6. Revised Final Proposal – 25 Days

Following the client’s feedback, the project is revised to a focused 25-day Phase 1 launch. The core e-commerce functions remain, while SMS is deferred and development effort is reduced.

## 6.1 Revised Scope

Keep: product catalog, product details, cart, checkout, mobile banking/payment, COD, EMS shipping, email notifications and SSL.

Remove from Phase 1: SMS notifications.

Prioritise essential UI and e-commerce functions required for Eid launch.

Defer advanced/non-essential enhancements to Phase 2.

## 6.2 Revised Schedule – 25 Days

| Period | Milestone / Activities | Output |
| --- | --- | --- |
| Days 1–5 | Final requirements, UI setup, hosting, WordPress/WooCommerce setup and theme configuration. | Approved setup + base UI |
| Days 6–10 | Homepage, categories, product catalog, product details and responsive design. | Completed catalog |
| Days 11–15 | Cart, checkout, COD and payment gateway integration. | Working ordering/payment flow |
| Days 16–20 | EMS shipping, email notifications, SSL, admin setup and integration testing. | Integrated store |
| Days 21–23 | Functional, responsive, security and browser testing; bug fixing. | Tested release candidate |
| Days 24–25 | Client review, final corrections, deployment and handover. | Live website + handover |

## 6.3 Revised Budget – Approximately BDT 1,32,000

| Cost Item | Calculation / Adjustment | Amount (BDT) |
| --- | --- | --- |
| Development effort | 155 hours × 500 | 77,500 |
| Hosting + domain | Optimised package estimate | 15,000 |
| SSL certificate | Reduced/essential SSL provision | 3,000 |
| Payment API setup | Retained for required payment integration | 20,000 |
| Tools / software | Reduced to essential tools | 5,000 |
| Subtotal |  | 1,20,500 |
| Contingency | 10% of revised subtotal | 12,050 |
| Revised Total |  | 1,32,550 |

Revised total = BDT 1,32,550, which is approximately BDT 1,32,000 and represents about a 19.7% reduction from the original BDT 1,65,000 proposal.

## 6.4 How the 20% Cost Reduction Is Achieved

Development hours reduced from 200 to 155 by focusing on core launch features.

SMS is removed from Phase 1 and moved to future improvement.

Tools/software allowance reduced from BDT 10,000 to BDT 5,000.

SSL allowance reduced from BDT 5,000 to BDT 3,000.

Non-essential features are deferred to Phase 2.

The revised budget is BDT 1,32,550 versus BDT 1,65,000 initially proposed.

## 6.5 Revised Risk Management

| Risk | Revised Mitigation |
| --- | --- |
| Compressed 25-day schedule | Prioritise must-have features, daily task tracking and rapid client approvals; avoid non-essential changes. |
| Payment API delay | Request credentials and sandbox access at project start; test payment integration as early as possible. |
| Client content/approval delay | Set fixed content submission dates and use placeholder content where appropriate. |
| Scope creep | Apply change-request policy; move new features to Phase 2 unless approved with timeline/budget impact. |
| Launch defects | Use staging, backup, browser/mobile testing and final acceptance checklist before deployment. |

## 6.6 Revised Service Agreement

| Term | Revised Agreement |
| --- | --- |
| Phase 1 Scope | Core WooCommerce e-commerce website only; SMS excluded. |
| Timeline | 25 calendar days, subject to timely client inputs, credentials and approvals. |
| Budget | BDT 1,32,550 estimated project total, approximately BDT 1,32,000 target. |
| Payment | 40% advance; 40% after core functions; 20% at final delivery/handover. |
| Changes | Scope changes require written approval and may add cost/time. |
| Support | 30-day corrective warranty for delivered functionality. |
| Phase 2 | SMS, mobile app/PWA and advanced features to be quoted separately. |

# 7. Final Acceptance & Handover Checklist

☐ Requirement gathering form completed

☐ Requirements assessed for clarity, feasibility and completeness

☐ Confirmed requirement summary completed

☐ Open-source vs close-source comparison included

☐ All 10 proposal elements included

☐ Initial budget breakdown included

☐ At least 3 project risks and solutions documented

☐ Service agreement included

☐ Client feedback recorded: cost, timeline and SMS

☐ Revised proposal prepared

☐ Revised budget shows approximately 20% reduction

☐ Revised schedule shows 25 days

☐ SMS moved to Phase 2/future improvement

☐ Final testing and client acceptance completed

☐ Handover credentials/documentation provided securely

# 8. Approval / Sign-off

| Role | Name | Signature | Date |
| --- | --- | --- | --- |
| Client Representative |  |  |  |
| Project Manager / Developer |  |  |  |